## Financial Snapshot
Cherrelyn — Financial Snapshot
Source: Colorado 7-Pack P&L, trailing 12 months (Mar 2025–Feb 2026), accrual basis.
Profit & Loss
Total Revenue | 24211360 | 100%
Total Operating Expense | 20302792 | 83.9%
Adjusted EBITDA (before management fee) | 3908569 | 16.14%
Management Fee | 1291699 | 5.34%
EBITDAR (rent-coverage pool) | 2616869 | 10.81%
Depreciation & Amortization | 443718 | 1.83%
Net Income | 2154409 | 8.9%
Gross Room & Board by Payer (skilled mix is the lever)
Payer | Gross R&B $ | % of R&B
Medicaid (incl. settlement) | 21350667 | 82.97%
Private | 1433549 | 5.571%
Hospice | 972063 | 3.777%
Medicare A | 1151080 | 4.473%
Medicare Advantage (HMO) | 826822 | 3.213%
TOTAL gross R&B | 25734181 | 100%
Skilled mix (Medicare A + MA) ≈ 8% — industry healthy = 15–25%.
Cost & Risk Flags
Total clinical/nursing dept expense | 14618652 |  | 72% of opex; CNA labor alone $3.84M
Director-level overtime (RN+LPN dir) | 234288 |  | Signals open positions / unstable scheduling
Bad debt expense | 442677 |  | ~1.8% of revenue; Medicaid-pending conversion
MDS RN labor | 12399 |  | Thin vs $20M+ Medicaid; case-mix accuracy = rate
Respiratory/O2 revenue | 2416590 |  | Specialty asset — leverage for skilled referrals
KNOWN (from acquisition due-diligence 'Sheet1'):
• 190 licensed beds; 173 occupied = 91% occupancy (~17 empty beds)
• Skilled mix 7.3% • Turnover 37.4% (below 44.4% national avg)
• CMS Overall 4-star (Health Insp 4 / QM 3 / PBJ-Staffing 2)
• Medicaid: $0 P4P, ~$19 ppd acuity adj. removed in model, $10 ppd high-utilization add-on
STILL CONFIRM DAY ONE:
• Last full survey date & 2567 results
• Agency/contract labor usage
• Actual Part B respiratory collection rate
• CHOW / new-system cutover date & owner
REVISED FROM THE FULL ACQUISITION P&L — 8/30/26 (601ch, Mar25–Feb26, accrual)
The snapshot above reconciles exactly to the GL. What the line-level detail changes:
1. Part B respiratory is ACCELERATING — the TTM basis understates the Day-1 exit
Gross 4543-0040, Sep 2025 | 93700
Gross 4543-0040, Feb 2026 | 284775
Growth over 5 months | 203.9% |  | No corresponding change in census.
TTM monthly average | 145216.4167 |  | A level not seen since December.
Net forgone — TTM basis (what the model carries) | 735375.934
Net forgone — Jan/Feb run-rate basis | 1324552.5
Understatement | 589176.566 |  | Larger than the entire overtime lever.
Blended Part B realization H1 vs H2 | 42.3% / 42.1% |  | Rate is stable — the basis is the problem, not the rate.
2. Overtime base is 5.8x the figure this plan named
Director OT (5111+5140) — as stated above | 234288
Building-wide OT, all 24 departments | 1355761
Director OT as share of the real base | 17.28%
CNA overtime alone (largest single line) | 452339 | 33.36%
Building OT % of worked payroll | 11.48% |  | Confirms the 11.3% stated in diligence.
Nursing OT % of nursing worked payroll | 15.63% |  | Confirms the 15.3% stated in diligence.
Agency / contract-nursing accounts in the GL | NONE |  | Overtime IS how this building flexes. Cutting OT without filling vacancies re-emerges as agency spend.
3. Skilled mix — already past the model's Upside case
Skilled ADC embedded in the P&L year | 13.4
Skilled ADC, 2026 Q1 actual | 22
Incremental ADC already won | 8.6 |  | Model Upside assumed +6. Skilled mix 7.8% (P&L yr) → 12.3% (2026 YTD).
Break-even ADC to offset Part B at run-rate | 11.3 |  | GAP OF 2.7 ADC (~$256K/yr). Under the old TTM math break-even was 5.1 and this was covered twice over.
4. New lever this plan omits — Medicaid case-mix capture (CO135, 10/1/25)
Residents on the listing / average CMI | 162 / 1.7143
Residents below a 1.20 index | 36 | 22.22%
Medicaid days per year | 54326
MDS RN labor (5112) against a $20M+ Medicaid book | 12399
Illustrative value of +0.05 CMI | 313953.8557 |  | PLACEHOLDER — needs the Colorado nursing-component rate. Do not bank.
5. Risks now quantified
Private-pay erosion (4,795 days CY23 → 3,529 TTM) | -513996 |  | Masked by Medicaid backfill; occupancy never moved.
Survey: 2567 of 1/30/25 — 5 tags, F880 infection control at E | OVERDUE |  | Recert 19 months out vs a 9–15 month cycle. An admissions hold hits the skilled census this plan depends on.
Turnover conflict — profile 37.4% vs prior plan 61% | RECONCILE |  | The OT case rests on which is true: 37% = scheduling problem, 61% = retention problem.
Rate assumption: implied Medicare A $383/day vs Medicaid $393/day |  |  | Model assumes a $400 differential. Confirm real CO rates — the largest single lever depends on it.
STILL CONFIRM DAY ONE (revised)
• Colorado rate sheet: Medicare A / Managed Care / Medicaid per diems + nursing-component rate per CMI point
• Actual cash collected on 4543-0040 separated from therapy Part B (42.2% is a blended Part B rate)
• Scope decision in writing: respiratory Part B only, or all Part B (therapy Part B = $1,198,390 gross / ~$505,700 net)
• Respiratory therapy wind-down cost — severance is excluded from every scenario
• Payroll/termination report to settle 37.4% vs 61% turnover
• A/R aging behind the $442,677 bad-debt line

## EBITDAR Bridge
Cherrelyn — EBITDAR Bridge (revised)
Part B priced off the Jan–Feb 2026 run-rate rather than the TTM average. Skilled-mix lever restated to census already achieved. Case-mix lever added.
Driver | Conservative | Base | Upside | Basis
Baseline EBITDAR (TTM per P&L) | 2616869 | 2616869 | 2616869 | 6100-9999
Part B respiratory net forgone | -1141679 | -1324552 | -1324552 | 3-month / Jan-Feb run-rate gross × 42.2%
Respiratory therapy labor offset | 208391 | 250069 | 277854 | 60 / 72 / 80% of 5113 labor $347,318
Overtime reduction | 150000 | 250000 | 350000 | 11 / 18 / 26% of the $1,355,761 OT base
Skilled mix — hold the recovery | 408070 | 612105 | 816140 | 50 / 75 / 100% of the +8.6 ADC already won
Medicaid case-mix capture | 0 | 156977 | 313954 | +0.05 CMI illustrative — rate unconfirmed
Total EBITDAR change | -375218 | -55401 | 433396
PRO FORMA EBITDAR | 2241651 | 2561468 | 3050265
Original model, same case | 2429684 | 2761162 | 3078747 | From the EBITDAR Impact Model as received.
Difference (effect of repricing Part B) | -188033 | -199694 | -28482
BREAK-EVEN CHECK
EBITDAR per added skilled ADC | 94900 |  |  | $400 differential × 365 × 65% margin. RATE UNCONFIRMED.
Skilled ADC needed to offset the Part B exit | 11.3223 |  |  | Base case, net of the RT labor offset.
Skilled ADC already achieved | 8.6 |  |  | 2026 Q1 (22.0) less the P&L-year baseline (13.4).
GAP | -2.7223 | -258343 |  | What overtime and case-mix capture exist to close.

## 100-Day Plan
Cherrelyn — Executive Director 100-Day Plan
Priorities derived from the P&L. Phased: Listen & Stabilize → Diagnose & Quick Wins → Execute & Lock-In.
Phase | Workstream | Priority | Action | Why (data driver) | Success Metric | Status | EBITDAR Impact ($/yr)
Days 1–30 Listen & Stabilize | Transition / CHOW | High | Confirm CHOW status: license, Medicare/Medicaid provider agreements, bank/payroll/AP/AR cutover, vendor novation. Build a cutover checklist with owners. | File is a GL re-mapping for new ownership — conversion risk is live | Zero payroll/billing disruptions; signed cutover checklist | Not started | CHOW — protects all of it
Days 1–30 Listen & Stabilize | People & Team | High | Meet every IDT lead 1:1; assess DON/MDS/Therapy/Business Office. Identify open positions and flight risks. | Director OT $234K signals instability/vacancies | Org chart with vacancies + retention-risk read; stay conversations done | Not started
Days 1–30 Listen & Stabilize | Clinical & Quality | High | Pull CMS star rating, last survey 2567, QAPI, and current census/payer-mix report. | Star rating & beds/census not in file; drive referrals & survey risk | Baseline dashboard: census, payer mix, stars, deficiencies | Not started
Days 1–30 Listen & Stabilize | Financial / Rev Cycle | Med | Review AR aging, Medicaid-pending list, and private-pay collections with Business Office. | Bad debt $443K (~1.8% rev) | Medicaid-pending and >90-day AR quantified | Not started | Bad debt $442,677
Days 1–30 Listen & Stabilize | Census & Payer Mix | High | Map referral sources (hospitals, MA plans); learn why skilled admits are low. | Skilled mix ~8% vs 15–25% target | Referral-source list + barriers documented | Not started | Skilled ADC worth $94,900 each
Days 31–60 Diagnose & Quick Wins | Census & Payer Mix | High | Launch skilled-mix push: market the respiratory/pulmonary + in-house therapy capability to hospital case managers and MA plans. | $2.4M resp/O2 revenue + full therapy = under-used skilled asset | ≥2 new/renewed referral relationships; skilled admits trending up | Not started | $408K – $816K
Days 31–60 Diagnose & Quick Wins | Financial / Rev Cycle | High | Stand up MDS/case-mix accuracy audit; tighten triple-check and ADL capture. | MDS RN labor only $12K vs $20M+ Medicaid; case-mix = rate | Case-mix index baseline + audit cadence; rate uplift identified | Not started | $0 – $314K illustrative
Days 31–60 Diagnose & Quick Wins | People & Team | High | Attack overtime: schedule rebuild, fill key vacancies, reduce agency reliance. | Director OT $234K; CNA labor $3.84M | OT $ down vs baseline; vacancy rate down | Not started | $150K – $350K
Days 31–60 Diagnose & Quick Wins | Financial / Rev Cycle | Med | Drive Medicaid-pending conversions and private-pay collection workflow. | Bad debt $443K | Pending backlog cut; bad-debt run-rate improving | Not started | Bad debt $442,677
Days 31–60 Diagnose & Quick Wins | Clinical & Quality | Med | Address any survey deficiencies; verify QAPI is active; staff/family town halls. | Stars gate MA contracts & referral flow | POC on track; town halls held | Not started | Census protection
Days 61–100 Execute & Lock-In | Census & Payer Mix | High | Formalize skilled-mix growth plan with targets; pursue/level-up MA contracts. | 2–3x Medicaid rate; biggest EBITDAR upside | Skilled mix % target set & climbing; MA contract progress | Not started | $408K – $816K
Days 61–100 Execute & Lock-In | Financial / Rev Cycle | High | Build the FY operating budget reflecting new ownership cost structure incl. rent/debt service vs EBITDAR. | EBITDAR $2.6M is the rent-coverage pool post-acquisition | Approved budget; rent/debt coverage modeled | Not started | Rent coverage on $2.24M – $3.05M
Days 61–100 Execute & Lock-In | People & Team | Med | Lock leadership: succession/development for DON, MDS, Therapy, Business Office. Confirm incentive plans. | Admin bonus $225K — align incentives to skilled mix & OT goals | Development plans + aligned incentive structure | Not started | $225K bonus pool re-pointed
Days 61–100 Execute & Lock-In | Clinical & Quality | Med | Set quality roadmap to protect/raise star rating (key to MA & referrals). | Stars drive payer access | Quality targets + owner per measure | Not started | Census protection
Days 61–100 Execute & Lock-In | Leadership | Med | Publish 12-month strategic plan + KPI dashboard (census, skilled mix, OT, AR, stars, EBITDAR). | Operationalize the data levers | Live monthly KPI dashboard | Not started
ADDED FROM FULL P&L DILIGENCE — 8/30/26
Days 1–30 Listen & Stabilize | Financial / Part B | CRITICAL | Stop billing Medicare Part B respiratory (4543-0040) at close. Decide IN WRITING whether the exit covers therapy Part B (4544/4545/4546-0040) as well. Wind down RT labor against the 72% of respiratory revenue Part B represented; cost the severance. | Gross billing tripled Sep 25 → Feb 26 ($93,700 → $284,775). TTM basis understates the exit by up to $589,176. | Billing stopped Day 1; scope decision documented; wind-down plan costed | Not started | ($1.07M) net of RT offset
Days 1–30 Listen & Stabilize | Financial / Rate Confirmation | CRITICAL | Obtain the Colorado rate sheet: Medicare A, Managed Care and Medicaid per diems, plus nursing-component rate per case-mix point. | Model assumes a $400/day differential; P&L ÷ census days implies $383 Medicare A vs $393 Medicaid. The largest lever is unverified. | Real per diems confirmed; bridge restated | Not started | Validates $408K – $816K
Days 31–60 Diagnose & Quick Wins | People & Team | CRITICAL | Schedule rebuild reaching the CNA line — $452,339 of OT sits there, a third of the building total. Fill the vacancies driving OT BEFORE cutting OT. | Building OT is $1,355,761 across 24 departments — 5.8x the $234K director figure. No agency account exists in the GL. | OT tracked weekly by department vs the $1.36M base | Not started | $150K – $350K
Days 31–60 Diagnose & Quick Wins | Financial / Case Mix | High | Chart-audit the 36 residents below a 1.20 case-mix index against ADL/Section GG, restorative and behavior coding. Resource the MDS function. | CO135: 162 residents at 1.7143 avg; 22.2% below 1.20. MDS RN labor only $12,399/yr against 54,326 Medicaid days. | Low-index cohort audited; CMI baseline + audit cadence set | Not started | $0 – $314K illustrative
Days 31–60 Diagnose & Quick Wins | Census & Payer Mix | High | Diagnose private-pay erosion before setting a target: referral drift, rate position, or faster Medicaid conversion. | Private days fell 4,795 (CY23) → 3,529 (TTM) = −1,266 days ≈ $514K at the $406 implied rate. Hidden by Medicaid backfill. | Cause named; stabilization target set | Not started | ($514K) exposure
Days 1–30 Listen & Stabilize | Clinical & Quality | High | Reinstate the F880 infection-control audit cadence (EBP gown/glove, pre-meal hand hygiene). Mock survey against all five 2567 tags by day 21. | 2567 of 1/30/25: 5 tags, F880 at scope E. Recert is 19 months out against a 9–15 month cycle — overdue. | Mock survey complete; audit cadence live | Not started | Protects the skilled census
Days 61–100 Execute & Lock-In | Financial / Rev Cycle | CRITICAL | Rebuild the FY budget on the ACTUAL post-exit run-rate, not the TTM P&L. Model rent and debt service against pro-forma EBITDAR of $2.24M–$3.05M, not the $2.62M baseline. | Pro forma is $2,241,651 / $2,561,467 / $3,050,265 — the Base case is essentially flat to today. | Approved budget; rent/debt coverage modeled on post-exit reality | Not started | Coverage on $2.24M – $3.05M

## Week-by-Week
Cherrelyn — Week-by-Week 100-Day Calendar
Start: Sat 8/1/2026 • Day 100: Sun 11/8/2026 • Cherrelyn = flagship of the acquisition.
Week | Dates (2026) | Phase | Theme | Key Actions | Milestone / Deliverable
Wk 1 | Aug 1–7 | Days 1–30 Listen & Stabilize | Land & secure the transition | • Day-1 CHOW continuity check: payroll, billing, provider agreements, bank/AP/AR all live • All-staff intro; walk every unit and every shift (incl. nights & weekends) • Meet DON day one; confirm clinical & staffing status • Pull baseline reports: census, payer mix, star rating, last survey 2567 | Cutover checklist with owners; zero payroll/billing disruption
Wk 2 | Aug 8–14 | Days 1–30 Listen & Stabilize | Meet the team | • 1:1 with every IDT lead (DON, MDS, Therapy, Social Services, Business Office, Dietary, Maintenance, Activities, HR) • Identify open positions & flight risks; start stay conversations • Review AR aging + Medicaid-pending list with Business Office • Close out any lingering CHOW/system glitches | Org chart w/ vacancies & retention-risk read
Wk 3 | Aug 15–21 | Days 1–30 Listen & Stabilize | Clinical & compliance baseline | • Review QAPI, survey readiness, F-tag history; meet Medical Director • Shadow MDS process; sit in on a triple-check / Medicare meeting • Map referral sources (hospitals, MA plans); learn why skilled admits are low • Confirm bed count & occupancy; flag empty beds | Baseline clinical dashboard + referral-source map
Wk 4 | Aug 22–28 | Days 1–30 Listen & Stabilize | 30-day read-out | • Synthesize findings into a baseline dashboard (census, payer mix, OT, AR, stars) • Pick top 3 vacancies to fill; launch recruitment • Finalize the quick-wins list | 30-day report to ownership/regional
Wk 5 | Aug 29–Sep 4 | Days 31–60 Diagnose & Quick Wins | Attack overtime & staffing | • Rebuild schedules; cut director-level OT (~$234K) and agency reliance • Fill priority vacancies • Stand up a daily labor-management standup | OT trending down vs baseline
Wk 6 | Sep 5–11 | Days 31–60 Diagnose & Quick Wins | MDS / case-mix accuracy | • Launch MDS audit; tighten ADL capture & triple-check • Establish case-mix index baseline; identify Medicaid rate uplift • Resource the MDS function (it's thin vs $20M+ Medicaid) | Case-mix baseline + audit cadence; rate uplift quantified
Wk 7 | Sep 12–18 | Days 31–60 Diagnose & Quick Wins | Skilled-mix push I | • Market respiratory/pulmonary + in-house therapy to hospital case managers • Meet top referral sources in person • Confirm clinical criteria/capability to accept higher acuity | ≥2 new/renewed referral relationships
Wk 8 | Sep 19–25 | Days 31–60 Diagnose & Quick Wins | Revenue-cycle tightening | • Drive Medicaid-pending conversions; fix private-pay collection workflow • Review bad-debt run-rate ($443K baseline) • AR >90-day reduction plan | Pending backlog cut; bad-debt improving
Wk 9 | Sep 26–Oct 2 | Days 31–60 Diagnose & Quick Wins | Quality & survey | • Address any deficiencies; verify QAPI is active • Hold staff & family town halls • Prepare 60-day read-out | 60-day report; POC on track
Wk 10 | Oct 3–9 | Days 61–100 Execute & Lock-In | Skilled-mix push II / MA contracts | • Pursue / level-up Managed Care contracts • Set a skilled-mix % target; track admits weekly • Formalize referral relationships | Skilled mix % target set & climbing
Wk 11 | Oct 10–16 | Days 61–100 Execute & Lock-In | Build the FY budget | • Build operating budget on the new ownership cost structure • Model rent/debt service against EBITDAR ($2.6M coverage pool) | Draft FY budget w/ rent/debt coverage
Wk 12 | Oct 17–23 | Days 61–100 Execute & Lock-In | Lock leadership | • Development/succession plans for DON, MDS, Therapy, Business Office • Align incentive/bonus plans (~$225K pool) to skilled-mix & OT goals | Development plans + aligned incentives
Wk 13 | Oct 24–30 | Days 61–100 Execute & Lock-In | Quality roadmap & KPIs | • Quality roadmap to protect/raise star rating; owner per measure • Stand up a live monthly KPI dashboard | Live KPI dashboard (census, skilled mix, OT, AR, stars, EBITDAR)
Wk 14 | Oct 31–Nov 6 | Days 61–100 Execute & Lock-In | 12-month strategic plan | • Publish the 12-month strategic plan • Present to ownership | Approved 12-month plan
Wk 15 | Nov 7–8 | Days 61–100 Execute & Lock-In | 100-day milestone (Day 100 = Nov 8) | • Final 100-day report: wins vs baseline • Set next-quarter priorities | 100-day read-out delivered